#### Senate

Subject: 	Annual Plan for Health, Safety and Environment Office – Review of progress in 2008/9 and new targets for 2009/10

Origin: 	Health, Safety and Environment Manager

Purpose of the report

To review the progress made on the annual plan for 2008-2009 and to set out a programme of work for the year October 2009 – October 2010.

Background

An annual plan of work is needed to ensure that the University continues to fulfil it statutory duty for the health, safety and well being of its staff, students and others affected by its activities. The plan shall ensure that the work of the HS and E Office supports the strategic planning of the university and makes best use of the resources available.

Points to note:

Section A of this report reproduces the annual plan for 2008/9 as the shaded sections of a table. An additional column on the right hand side shows the progress made against each target.

Section B of the report shows the annual plan 2009/10

It should be noted that the progress report this does not show the work that has been carried out in 2008/9 over and above those items identified in the annual plan for this period. This includes but is not restricted to :

- Handling routine service requests from departments

- Monitoring of weekly fire tests to ensure that all buildings carry out their alarm tests at the designated time

- Attendance at departmental safety committees – increased involvement in 2009

- Continuing to develop formal and informal ties with the University Insurer UMAL. This year saw UMAL conduct their periodic audit of the University (3 year cycle)

- Review of all University radiation protection arrangements. A planned audit by the Environment Agency will take place on October 16th 2009 – a report on this visit is covered as agenda item SAF-09-P

- Moving offices – this provided an opportunity to review administrative tasks and record keeping

- The Occupational health database has been revised and updated.  This will increase the breadth of data which is stored and will allow more detailed reports to be generated

- Hand Arm Vibration training conducted for all operational staff in Facilities Management exposed to vibration in their current or previous work.

- Re establishing the laser safety technical group

A)  Review of Progress Made Against the Annual Plan 2008/9

Health and Safety (Fire)

| Aim | Target | Comment | Progress |
| --- | --- | --- | --- |
| To complete targets from 2007/8 | Complete second round risk assessments Complete review of signage Check hydrant flow – needs to be coordinated with Facility Management to ensure that there is no interruption to normal business | Work has to be programmed around access to buildings. Higher risk priorities were addressed in 2007/8 – in particular residential accommodation. Remaining premises will be scheduled according to risk | Second round risk assessments mostly are completed (exceptions are those areas where building work is planned that will substantially alter the fire risk assessment.) Fire hydrant flows have been checked Fire signage is up to date in all major buildings (approximately 80% of the building stock.) |
| Improvement to the fire alarm systems across campus | Support Facilities Management to proceed with the second staff of the plan to upgrade the fire systems | The programme to upgrade fire alarm systems is staged according to risk based priorities determined by fire risk assessments. The first stage of work has been This work is on-going to upgrade the next series of buildings | The second stage of the programme to have automatic fire detection in all significant buildings will be completed by the end of November 2009. It should be noted that 3 times in the last 12 months newly installed AFD has detected fire at early stages in areas where it would previously have resulted in a more substantial fire. |
| Monitor compliance with LU fire strategy adopted in 2007/8 | Report to HSE committee in 2009 | To be monitored as part of the fire risk assessment process/ work to prepare PEEPs and by liaison with FM on new build and refurbishment projects | Completed in 2009 |
| Incorporate fire training into the training matrix – see training | Identify which groups of staff require mandatory fire training – e.g. fire extinguisher training for all technicians and research staff using flammable material. Incorporate this information into the matrix To purchase and make available an electronic hosted training package that will provide suitable and sufficient fire safety awareness training for all staff/(students?) | A remaining difficulty is to determine how training records can be matched against the training matrix. Article 21(2)(d) of the Regulatory Reform(Fire Safety) Order 2005 requires the responsible person to provide fire safety training to employees in a manner appropriate to risk. E-training with a management package will allow this training to be delivered and monitored efficiently | Fire extinguisher training continues to be delivered to all fire marshal, wardens and sub wardens. Fire extinguisher training for technical and research staff is still optional but is strongly encouraged. Sufficient courses have been made available to train all staff. E-Training is being developed and will be in place before end of 2009. (SCORM compliant and compatible with the Learnserve.) |
| Business Continuity | Fire service information packs to be provided in all higher risk buildings – chemistry, S building, Wolfson etc Some departments (Chemistry and Wolfson ) have been proactive in reviewing business continuity risk from fire in buildings. Departments will be contacted to discuss protection of key assets | The University is reviewing business risk as part of the emergency plan overhaul. This work to provide fire service information packs should ensure that wherever possible the maximum effort can be expended by the fire service to fight fire in buildings. If this information is not provided there maybe a reluctance on the part of the fire service to commit fire crews into buildings with unknown fire risk. | The final version of the pack was agreed in October 2009. The information packs will be compiled for selected high risk buildings in 2009/10 to enable the fire service identify risks and assets. – Keeping this information up to date will be a challenge but as a minimum annual reminders will be sent out to HoD to remind them that changes made to risks or assets should be reflected in the fire service plan for their buildings |

Health and Safety (General)

| Aim | Target | Comment | Progress |
| --- | --- | --- | --- |
| Audit | To continue with the HASMAP audit where this applies to the remaining large departments – Wolfson School, LUSAD and SDC and those departments with higher risk activities. Audit reports will be presented to HSE committee and progress monitored For smaller departments and those engaged in less hazardous work it has been recognised that targeted audits are appropriate and a separate scheme shall be adopted to measure compliance/assurance |  | Wolfson School audit completed using HASMAP. All targeted audits carried out as planned. Further mini audits are planned for 2009/10 |
| Improving communications with departments | To continue the work started in 2007/8 and build on the DSO forum, training and regular formal and informal contact -weekly contact by e-mail, safety committee attendance and newsletter. |  | All targets met for 2009/10. This work is on-going and positive feedback has been received from Departmental Safety Officers. |
| Policy and website | To replace remaining policies back onto the website To undertake the 2 yearly review of the Health and Safety Policy To investigate the successful transition of University Policy into local arrangements . | This target is scheduled for February 2009 HSE meeting | More than 80% complete. There are still some guidance documents to be reviewed and put back onto the website. These will be reviewed in 2009/10. Review of the Health and Safety Policy is an agenda item for October 2009 |
|  | Manual Handling PPE Biological safety Work away from the University – incorporate new guidance on placement students, fieldwork and other existing arrangements on lone working and work overseas | Update current arrangements Update current arrangements New policy Request from PVC Teaching and Learning | The draft policy concerning working overseas has not yet been finalised. This will be rolled forward to 2009/10/ All other targets have been met |
| DSEAR /Gas safety | Develop training Audit compliance with the new DSEAR policy – latter part of 2009 |  | Compliance with the DSEAR policy is scheduled to be reviewed in November |
| Environmental activity | Adopt the epiGenesys training and management system for clinical waste- £9000 Review arrangements for managing other hazardous waste Other targets to be developed in conjunction with Sustainability Coordinator. | Hazardous waste costs rose by 33% 2006/7 to 2007/8. Budget is now £30,000 | An assessment was carried out to provide assurance that the University’s Duty of Care as a generator of hazardous waste is met. Hazardous waste was tracked to verify that once it has been collected from the University by a registered waste carrier it is transferred to an appropriate facility for treatment and disposal. This assessment provided the required assurance. The University is seeking to attain an Eco Campus award and the HSEM is contributing to this target |

Occupational Health

| Aim | Target | Comment | Progress |
| --- | --- | --- | --- |
| Facilitate departmental compliance with the Hand-Arm Vibration policy | To complete the current programme of health surveillance for Facilities Management and agree a basis to carry this forward on an on-going basis To consult with department and make suitable arrangements to implement the policy | The Occupational Health Advisor has a separate and ambitious programme of work. These targets have been picked out to address some of the bigger projects | The Occupational Health Advisor has made considerable progress in developing the University’s Occupational Health service. The Hand Arm Vibration assessments have been completed. An updated HAVS policy was produced that was scrutinised and approved by the Health and Safety Executive. All operational staff in FM have had training. The HAV arrangements will now be rolled out to other departments in 2009/10 |
| Stress | To work with HR and develop the University Stress Policy in line with the findings of the staff survey. |  | On- going. A new stress management course aimed at managers is being piloted in November. |
| Review university arrangements for management of risks to pathogens and Blood Borne Viruses | Review the existing policy in the light of Biological Safety Policy |  | Done – agenda item for October 2009 |

Occupational Hygiene

| Aim | Target | Comment |  |
| --- | --- | --- | --- |
| On-going from 2007/8 – to provide an in-house resource for monitoring workplace contamination and environmental conditions | For staff in HSE to undertake the following British Occupational Hygiene Society modules: M102 Measurement of Hazardous Substances (including Risk Assessment) M103 Control of Hazardous Substances M201 Thermal Environment and Non-Ionising Radiation) S301 Asbestos and other fibres | Training need identified in 2007/8 The HSE office shall concentrate on in house service provision for the foreseeable future but there is scope to become a revenue earner by offering external consultancy in this area in the future. | M201 has been completed. Training providers for modules M102 and M 103 yet to be identified. The University asbestos policy is being reviewed by FM and HSE in November. This action point will be considered as part of the review |

Training

| Aim | Target | Comment |  |
| --- | --- | --- | --- |
| To coordinate and develop HSE training | To produce a training matrix with suitable training courses identified and made available to staff as either optional or mandatory dependent on the job role and risk. To develop systems for monitoring attendance on training courses To offer more in house training on core subjects and for this training to be publicised through staff development To use a wider range of means to deliver training – cascade training and e-training – fire awareness training is seen as a good pilot for e-training | A lot of health and safety training is carried out across the university that ensures staff are competent. Discussions with DSO has identified a need to coordinate the training that is offered to better use resources. Discussions with Loughborough College, as part of a HEFCE funded project , have suggested that more joint working on training delivery and collaboration may have benefits in terms of economies of scale. | Agenda Item October 2009 |

B)	Annual Plan 2009/10

Fire safety

| Aim | Target | Comment |
| --- | --- | --- |
| To build on and embed policies and procedures that have been developed to manage fire safety | Monitor compliance with the fire strategy for new build and for re furbishment work Training - fire marshal and extinguisher training for all technical staff and sub wardens Ensure fire panel training is carried out for all duty staff in residential accommodation Carry out checks on a newly installed refuge alert system Audit compliance with the University’s DSEAR policy Produce fire service plans for all high risk buildings so that assets are protected in a fire situation Keep fire risk assessments up to date and follow up action points Produce CAD plans for buildings in 2D and 3D Work with DANS to carry out Personal Emergency Evacuation Plans | The necessary structure to manage fire safety across the university has been put in place over the last 2 years. The fire safety targets for 2009/10 will ensure that these policies and procedures are working properly. |

Radiation Protection

| Aim | Target | Comment |
| --- | --- | --- |
| To provide assurance that radiation protection arrangements continue to meet the needs of the University | Review the University’s badging policy and designation of controlled or supervised areas | In 2008/9 the Radiation Protection Officer carried out a review of all documentation relating to radiation protection. In 2009/10 |

Radiation Protection Continued

| Aim | Target | Comment |
| --- | --- | --- |
|  | Audit departments with areas designated as “controlled” or “supervised” in accordance with the Ionising Radiation Regulation. Produce the Radon Survey Prepare for legislative changes resulting from the introduction of Environmental Procedures Permits in April 2010 – report to HSE committee | this work will be expanded by carrying out audits on site to ensure that working arrangements continue to be satisfactory. |

General Health and safety

| Aim | Target | Comment |
| --- | --- | --- |
| To build on and embed policies and procedures that have been developed to manage general health and safety | Use HASMAP on one department Conduct the following targeted audits: Risk Assessment Dangerous Substances Explosive Atmospheres Biological Safety – including holding 2 meetings of the Biological Safety Committee Control of Substances Hazardous to Health Provision and Use of Work Equipment Laser Safety Review event planning and risk assessment arrangements (in conjunction with Loughborough Students’ Union.) | A variety of audits were conducted in 2008/9 and it is the intention of the HSE department to Use HASMAP to audit the University’s management systems ensure compliance with University policies by targeting specific risk topics Use structured interviews /questionnaires to investigate the successful transfer of information to staff. |

General Health and Safety Continued

| Aim | Target | Comment |
| --- | --- | --- |
| Training | To ensure that courses specified in the 2009/10 training matrix are made available to target groups of staff | See training matrix 2009 |
| Environmental Protection | Develop hazardous waste management systems Contribution to Eco campus where appropriate Work with IT/FM to develop systems for managing Waste Electronic Electrical Equipment (WEEE) | These targets are the commitments agreed by the HSEM to contribute to a wider agenda of developing sustainability. |
| Laser Safety | To produce University guidance as standards for using lasers at Loughborough University | The laser safety policy was updated in 2009 but it is recognised that without supporting guidance there may be differences of opinion within the University concerning the practical application of this policy. Guidance based on BS 60825 will be drafted, circulated for consultation and agreed upon before being used for audit purposes. This work shall be reported upon in detail at the February meeting of the HSE committee |
| Accident reporting/investigation and first aid provision | Changes made to the way in which accident data is collected in 2009 will enable Loughborough University to make comparisons with similar institutions from Jan 2010. Review provision of first aid training to meet the needs of the university and to |  |

General Health and Safety Continued

| Aim | Target | Comment |
| --- | --- | --- |
|  | accommodate changes to the first aid at work regulations. Report to the HSE committee giving details of claims arising or concluding in the 2009/10 reporting period | HSE Approved Code of Practice on First aid Training has been amended and the schedules for initial training, interim training and refresher training have implications for the courses offered by Loughborough University |

Occupational Health

| Aim | Target | Comment |
| --- | --- | --- |
| To provide a service that continues to meet the needs of all service users. | Rolling out HAVS management procedures to a wider University population Audit Blood Borne Virus Policy | A new sickness absence management policy is being introduced by Human Resources. This will have resource implications for the Occupational Health service. Any plans to develop this service will be constrained by the additional workload and a further report will be made to the HSE committee in due course to expand on Occupational Health plans for 2009/10 |

HSE Office October 2009