Loughborough University

University Strategy 2006-2016

Implementation Plans

| 1. Progress Report on 2007/08 Priorities Please provide a report on progress against the priorities you identified for 2007/08 |
| --- |
| Learning & Teaching | Comments including specific target dates where applicable | Progress with reference to KPIs where appropriate - January 2008 |
| Curriculum Profile, Student Recruitment & WP |  |  |
| Develop History and associated programmes |  | Launch history in 2009; Feasibility funding released for Pharmacy proposal; Opportunities linked to ETI, bio-engineering, sustainability and nutrition under consideration. |
| Develop flexible forms of study particularly at PG level | Outcome- increased recruitment to flexible forms of PG study | Ford programme at UG level being developed – HEFCE contribution will monitor/evaluate and identify QA/QE resources required to sustain flexible provision at UG and PG levels. |
| Meet UK/EU UG recruitment targets at an acceptable standard | Outcome- encourage further raising of A level entry requirements | Strategic review of intakes and populations in hand. (Note: Average entry grades at institutional level increased in 2007/08 for 5th year running and now over 300 points) |
| Develop international foundation programme | Programme to be offered at Loughborough & Castle Colleges from 2007/08 – progression route to LU | Programme with colleges approved; External marketing and internal promotion in hand. Strategic approach to international foundations under discussion, linked to intakes/population review. |
| Increase FT recruitment at PG level | Investment in Graduate School and International Office | Increased investment in International Office approved; Alumni bursaries approved; PG scholarships in place; dedicated PG marketing budget in place through Director of Marketing and Communications. For UK/EU PGs, emphasis will be placed on flexible provision linked to employer engagement. |
| Implement new WP Action Plan | To include sports related WP activities | Programme for 2007/08 under way; Excellence Hub in place; Windsor Fellowship scheme agreed |
| Student Learning Opportunities |  |  |
| Develop international and enterprise components in the curriculum | Outcomes – increased % of programmes with study abroad, pilot projects on int. learning through Grad School, optional credit-bearing lang modules and enterprise education modules in selected UG programmes. | Strategic oversight of student/staff exchanges and study abroad proposed through formation of International Mobility Team. Discussions on the detail in hand. Pilot on international learning in hand with PGR students through Graduate School/Careers Centre. Strategic approach to enterprise education under discussion (Enterprise Implementation Plan) |
| Develop University (skills) award | Funded through TQEF | Draft proposal presented to PQT and under revision. Pilot to be launched in 2008/09. |
| Increase % of UG & PG undertaking sandwich and short work experience placements. |  | Discussions in hand |
| L&T Resources & Support |  |  |
| Evaluate and enhance induction |  | Induction Review Group recommendations followed up with relevant support services/LSU; Effective practice in academic departments being shared. |
| Establish Loughborough Student Hub |  | Proposals been developed, discussions taken place with relevant support services and Head of Marketing and Communications. It is hoped that a we version could be implemented in 2008. Wide promotion of concept within the University needs to be done. |
| Produce e-learning strategy |  | Draft strategy and action plan prepared and circulated to Faculties for comment. To be submitted to LTC on 14/2/08 for approval. |
| Establish University Centre for L&T | To enhance support for staff involved in T&L, collaboration & sharing of good practice | Strategic proposal developed and initial consultations taken place; Indicative priorities for 2008/09 been prepared together with resource implications; Documents to be submitted to LTC on 14/2/08 |
| 2. Initial Statement of Priorities for 2008/09 Please provide, in order of priority, an initial indication of proposed actions and their resource implications. Include any issues that have arisen from your consideration of the departmental development plans. NB Actions are listed under headings used in the Learning and Teaching Implementation Plan Two priority areas with specific resource implications are shown in brackets (1), (2) |
| Learning & Teaching | Comments including specific target dates where applicable | Possible Resource Implications |
| Curriculum Profile, Student Recruitment & WP |  |  |
| Continue subject/programme development |  | None at this stage |
| Implement outcome of strategic review of intakes/populations |  | None at this stage |
| Monitor Ford programme, assuming it is approved; Teaching Centre/Graduate School/EngCETL to support flexible provision (including blended learning) linked to employer engagement |  | HEFCE funding would contribute to this activity. Additional support for Graduate School may be necessary |
| Develop market research for student recruitment |  | Marketing and Communications/Registry |
| Outcome of discussions on international foundation programmes to be implemented |  | Resourced through International Office |
| Monitor and develop WP activity linked to recruitment to LU |  | Additional funding linked to the Access Agreement |
| Student learning opportunities |  |  |
| Evaluate pilot on international learning and develop in the curriculum beyond PGRs |  | None at this stage |
| Monitor and develop further study abroad/exchange opportunities |  | None at this stage |
| Develop approach to placement opportunities within UK and internationally |  | Additional resource may be required |
| Implement Enterprise Education strategy as appropriate |  | None at this stage |
| Evaluate Skills Award Pilot and prepare for wider launch |  | TQEF available for 2008/09 |
| Student learning resources and support |  |  |
| Develop induction across all 3 undergraduate years |  | None at this stage |
| Launch Student Hub |  | Additional resource may be required |
| Expand buddying scheme across the University |  | Additional resource anticipated |
| Further develop e-learning and lead initiatives |  | Appoint head of e-learning; Request that OLDO contracts be converted from fixed term to open ended (2) |
| Ensure library, IT resources, teaching rooms and flexible learning spaces continue to meet requirements of learning and teaching |  | Additional resources anticipated |
| Learning and teaching enhancements, staff recognition and reward |  |  |
| Launch Teaching Centre; review implications for QA aspects of quality management |  | Request that fixed term contracts funded through TQEF/RDS2 be converted to open ended; Request 2 additional posts; other budget matters to be resolved (1) |
| Appraise QA processes to ensure they are fit for purpose |  | None at this stage |
| Ensure current discussions on re-aligning rewards with University Strategy are implemented for staff in job family, teaching and research, and developed for all appropriate staff |  | None at this stage |
| 3. KPIs Please identify any changes/developments to KPIs in your area. |
| None |