Loughborough University

University Strategy 2006-2016

Implementation Planning Progress 2010/11

| Learning & Teaching |  |  |
| --- | --- | --- |
| Priorities | Target Dates | Progress |
| Curriculum Profile, Student Recruitment and WP |  |  |
| Continue programme development Conduct strategic programme review at UG and PG levels in relation to student demand. Particular attention will be given to the balance between new programmes and discontinued programmes Ensure PG Prospectus links University-wide research schools with associated PG programmes Promote PG programmes by key categories on ‘Impact’ website |  | Evaluation begun in context of restructuring and preparation for UG higher fees; action to continue in 2011/12 Audit conducted into sustainability in curriculum, building on 2008 study; significant developments identified Marketing and Communications alerted to need for PG programme promotion by category and strategic theme to be used in PG prospectus and related marketing materials |
| Develop and implement next phase of CPD provision linked to strategic partnerships and employer/employee engagement |  | Initiative not followed up in 10/11 with creation of new Schools and other priorities linked to |
| Review intakes/populations Agree intake targets across major categories with continued emphasis on intake quality (Minimum entry level of 300 points for all UG programmes, 2011/12) Develop and implement action plan for EU and international recruitment, including PGRs, in light of strategic review across departments Monitor changes to Tier 4 PBS visa system and implement as appropriate Continue to evaluate performance of LouColl IFP |  | Entry grades for 75 programmes across 8 departments increased for 2011 entry with introduction of minimum grade of BBB in all Science subjects. No evidence to date that applications affected Action Plan for EU and international recruitment agreed and implemented Strategic engagement with government scholarships/sponsoring bodies undertaken in relation to PGR and PGT recruitment, particularly in Middle East and South America Changes to Tier 4 PBS system been monitored and representation made as appropriate. Response made to consultation on changes to system. Current issues relating to changes from 21 April 2011 to English Language requirements being worked through Dialogue taken place with Loughborough College over measures to improve recruitment in 2011/12 |
| Agree objectives and monitor actions of Student Outreach and Recruitment Team Evaluate progress against approved strategic and operational objectives and HEFCE targets |  | Progress against Access Agreement targets monitored as part of monitoring return Monitoring against approved strategic and operational objectives commenced as part of Performance Development Review process, and will be enhanced in 2011/12 |
| Promote increasing cooperation between UG and PGT admissions teams with a view to creating a single integrated resource in 2012 Explore possibilities for further central processing of applications Develop wholly electronic UCAS applications system: scope project and design system in 10/11, for piloting in 11/12, and full implementation in 12/13 |  | Centralised decision making taken on for Social Sciences (UG and PGT) and Geography (PGT) Teams cooperated at peak times and in relation to move to Rutland Opportunities being identified to enhance integration following relocation |
| Student Learning Opportunities |  |  |
| Develop initiatives linked to international learning Continue work with Student Experience Team/Student Support Centre on languages at Loughborough Support development of subject-focused English language provision with an appropriate financial model Implement proposals for the expansion of foreign languages opportunities within and beyond the curriculum Raise profile of international/global perspectives in the curriculum Ensure promotional and QA dimensions of student exchanges/ international work placements/overseas vacation study visits remain integrated. Work with Director of Internationalisation Strategy and International Advisory Group on this |  | Student Support Centre conducted evaluation of English language support; opportunities/refinements identified Appropriate funding model agreed with Finance in relation to future development of subject-focused English language provision in the curriculum Uptake of UWLP strong in some Schools in particular. Regulations reviewed - opportunities available in UG programmes across all Schools (though not all programmes). Timetabling challenges identified of expanding significantly foreign language provision within the curriculum. Uptake of extra-curricular opportunities buoyant Languages opportunities within and beyond the curriculum promoted through LSU ‘Experience the World’ initiative New arrangements for QA and promotion of student exchanges etc working well |
| Further develop placement activities Monitor effectiveness of central network of placement support (including promotion, QA, health and safety) Offer informal training/advice sessions to new placement tutors Continue recently introduced practice of two meetings per year for placement tutors Enhance support for specific departments Continue to build database of placement opportunities in UK and internationally through liaison between Careers and Employability Centre (CEC) and Enterprise Office Maintain University Placement and Internship programme and expand with campus tenants |  | Series of major projects carried out through Placement Working Group to enhance institutional quality management of placements, ensure greater consistency in student experience, and increase range of opportunities Institutional support received for feasibility study/change project to recommend developments needed centrally and within Schools to ensure that from 2012 entry cohort all UG students have the opportunity to undertake a placement during their studies Formal approval given for LU graduate internship and UG placement scheme to be continued for a further year (2011/12), following success of scheme in 2010/11 |
| Continue to enhance Loughborough graduate and postgraduate prospects CEC to continue to build on its range of employability initiatives, including mentoring and work shadowing Investigate through CEC further ways to prepare students for the workplace- more ‘work-ready students and graduates Maintain sustainability and cross-cultural awareness initiatives as compulsory elements of Employability Award (See also Student Experience Implementation Plan) |  | CEC and Enterprise Office worked together on sharing employer contacts to benefit of graduates LU participated in Hefce Graduate Internship Scheme through CEC placing 24 graduates, most of whom were from LU Working Group established to explore opportunities to strengthen links with key employers in anticipation of higher UG fees Employability Award scheme now has 400 places available to undergraduate students each academic year Number of participants grown significantly; currently 660 students on award (May 2011) Review ongoing of student engagement and completion rates PG(T) model to be piloted in Autumn 2011 (Cross-reference with Student Experience Implementation Plan were Award also features) |
| Student learning resources and support |  |  |
| Further develop student engagement project In conjunction with Student Experience Team, evaluate induction website for new UGs and PGT students Promote induction activities with returning students Make refinements as appropriate for implementation in 2011 Develop peer support initiative if resources permit Work with pilot departments on CLEAR audit tool |  | Student induction website will be revised in late June/early July, as will Returning Students’ website, ready for 2011/12 Student induction checklist under revision, to be distributed to new Schools in August by Quality Enhancement Officer Further work needed on induction with returners Personal tutoring strand of student engagement project to be in 2011/12 following successful pilot in 10/11 Teaching Centre involved in STEM project on peer support led by MEC; training will be provided for student volunteers this summer in order that project can go live in 2011/12 Limited progress with CLEAR audit tool to date, in light of restructuring |
| Provide input to student portal discussions through successor to LUSI Steering Group Follow up study skills programme with University Library |  | Development and piloting of Student Portal underway; this will subsume Hub Work underway to embed within curriculum Support Services’ contribution to development of students’ academic/study skills |
| Ensure an integrated approach to development of the campus learning environment in collaboration with Director of Change Projects Follow up findings of Learning Landscapes Project Agree appropriate forum for discussion linking learning spaces, teaching rooms and e-learning Work with Timetabling Officer on staff teaching/learning space requirements |  | Membership of e-learning Advisory Group reflects integrated approach Teaching Support in FM to produce minimum specification for all pool rooms for discussion and agreement in 2011/12 Discussion will take place with new Schools in 2011/12 to identify priorities for development of informal learning spaces |
| Continue to develop strategic approach to E-Learning Generate policies relating to key areas, including open educational resources, use of 3rd party web 2 services, e-assessment Monitor use of technologies to support learning, including Echo 360 pilots and make recommendations as appropriate Evaluate DL projects funded in 09/10 Monitor and evaluate use of Learn by staff and students |  | Major project carried out on efficient use of learning technologies by academics to support effective student learning On basis of findings, draft e-learning strategy and implementation plan being drafted for consultation, agreement and launch in 2011/12 Evaluation considered by Operations Committee of DL projects supported in 09/10 through the University Strategic Fund. Important lessons learned if DL were to be expanded in course delivery, including the significant resource implications P/T DL programmes in engineering evaluated with current participants, including student experience, areas of good practice and for further development. |
| Learning & Teaching Enhancements, Staff Recognition and Rewards |  |  |
| Continue to develop enhancement projects linked to strategy Build on assessment work with departments carried out in 09/10 Work with Marketing and Communications to promote learning and teaching support network to academic staff including Teaching Centre, E-Learning Team and 2 Centres for Excellence |  | Progress on assessment criteria for substantive UG project modules reviewed at APR; further actions agreed at departmental level as appropriate New Lecturers’ Course now includes explicit reference to devising appropriate assessment criteria Audit of placement modules carried out – assessment criteria to be reviewed as part of the revision of module specs E-learning Team to be integrated with Teaching Centre from 2011/12 to enhance support for Schools; new Engineering Education Centre to be established building on outstanding reputation of EngCETL and Engineering Subject Centre hosted by LU |
| Continue to address recommendation of QAA audit Establish sub-committee with LouColl to oversee validations Prepare to reorganise internal QA systems and QE networks in response to changes in University structure Prepare to respond to current external reviews in relation to quality and standards (audit, academic infrastructure, external examining, TQI) Ensure that QA and student support responsibilities are clearly located within new structures |  | Teaching Partnerships Sub-Committee of LTC established to oversee all taught collaborative provision Series of major projects carried out linked to University restructuring (through a Learning and Teaching Working Group) to establish effective and efficient learning and teaching structures, processes and responsibilities across support services and new Schools Input provided to external reviews as appropriate and implications of findings considered |
| Further develop approach to recognition and reward Evaluate reaccredited New Lecturers Course and make modifications as appropriate Evaluate teaching section of new SL Promotion Scheme and make modifications as appropriate Implement revised promotion criteria for senior appointments Introduce new University award for outstanding academic practice |  | Feedback on NLC positive so far from range of sources; modifications made as appropriate Evaluation of teaching section of SL promotions planned for June/July 2011; changes anticipated in light of informal feedback; positive feedback of advisory interviews Revisions to personal chair criteria to be implemented in 2011/12 University award to be endorsed by LTC in June 2011; planned launch in 11/12; presentations at Degree Ceremonies |