3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| a) Failure to match UK/EU intakes with targets (Strategic) | 4,4 | Visibility & Image Volatile league table position | Focused student recruitment policy incl. intake targets Efficient and responsive admissions system Tailored schools liaison activities and interactions with selected schools/ colleges | 3 3,3 | Improve electronic student records to enhance accessibility to applicants and staff (IT Services 2010/11) | Tighter offer management during 2010/11 and close admissions management in August 2011 (SR Team) Work is underway in relation to target intakes in light of higher fees/graduate contribution in 2012/13 (SR /Planning) Work is underway to check tariff score for league tables to assess how it is calculated and whether the score is accurately displayed (SR/Planning) | 3,3 | Overall assessment of risk & response: Date of review: 9 June 2011 |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Marketing & Student Demand Lack of understanding of markets Slow response to changing patterns of student demand | Quality marketing Monitoring of applications and conversion trends Regular liaison between academic Schools and central admissions to ensure recruitment strategies are sensitive to market changes |  | Work underway on promotional aspects of recruitment (SR Team & Dir M/C 2010/11) Develop EU recruitment strategy (Int. Office 10/11) Develop the work of the integrated Student Outreach and Admissions (SOAR) Team (Registry 2010/11) | New group instigated to link Marketing and Recruitment/ Admissions in terms of strategy and policy and processes |  |  |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Academic Provision Restricted subject and product range leading to intake imbalances between programmes Failure to anticipate necessary prog. changes in relation to UK/EU market Significant move of applications from certain subjects to other subjects; possible significant overshoot in some Schools and undershoot in others | Regular programme evaluation in Schools Careful management of intakes at programme level by Schools |  | Strategic programme review (SR Team/ Faculties delayed until 2011) Further develop flexible approach to provision linked to strategic partnerships and employer engagement (SR Team/ Ent Office delayed until 2011) | Placement opportunities and support being enhanced (CEC, Registry 2010/11 & 2011/12) |  |  |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Funding Government fee structure & response of competitor institutions to this Uncompetitive bursary and scholarship schemes (Operational) Uncompetitive Access Agreement Inability to meet OFFA requirements Long term implications for Postgraduate demand in the new fee environment | Promotion of bursaries and scholarships funded internally Regular benchmarking to ensure bursaries and scholarships are competitive Monitor impact of higher tuition fees on interest in/demand for PG study Agree annual objectives and monitor actions of SOAR Team on a regular basis |  |  | Review Access Agreement - support package in relation to competitors (Access Group 2010/11 & 2011/12) Develop fair Access/Outreach activities with Schools (Acad. Registry/Schools 2010/11 & 2011/12) Implement focused marketing/recruitment strategy (Registry, Marketing/Comms Schools 2010/11 & 2011/12) Monitor performance against WP milestones (New Strategy Group 2011/12) |  |  |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| b) Failure to meet international recruitment targets (Strategic) | 4,5 | Visibility & Image Declining position in league tables Increased aggressive competition within and beyond UK Failure to respond speedily to student applications and enquiries in the face of continued significant growth in volume of applications (Operational) Failure to respond speedily to submission of results by students and subsequently converting them to UF Failure to issue CAS (for Tier 4 PBS visa purposes) in timely manner | Strategic international student recruitment policy incl. diversification Academic presence and presentations at key international fora & in overseas institutions Ensure good conversion rates by speedy response to enquiries, receipt of results and applications, and speedy issuing of CAS Promote increasing co-operation between the undergraduate and taught postgraduate admissions teams | 3,3 | Monitor improved online applications (Registry 2010/11) Develop alumni activity (Registry/ Alumni Relations 2010/11) | Enhance links between recruitment and broader internationalisation Strategy Current Monitor outcome of Tier 4 PBS visa system changes (2010/11 & 2011/12) | 3,3 | Overall assessment of risk & response: Date of review: 9 June 2011 |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Marketing & Student Demand Undue concentration on limited geographical markets and products Poor marketing and lack of understanding of markets Lack of awareness of changing international patterns of demand Websites inadequate and out of date Expansion of in-own country and regional HE provision Inability to pay agents in a timely manner | Quality marketing Development of appropriate and attractive degree programmes Effective use of overseas agents & focused recruitment missions Extended range of country visits Development of partnership links overseas Regular visits to UK FE, schools and Foundation colleges which cater for international students Continual contact with agent Promote international foundation with Lou. College New IO Website with video footage (talking heads) and translated pages (multi languages) |  | Develop Latin American links (IO/Schools 2011/12) |  |  |  |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Academic Provision Failure to anticipate changes in relation to Int. market e.g. Bologna Process | Close monitoring of national/ international responses to Bologna Process etc |  | Strategic programme evaluation linked to differential targets (Grad Sch – with ADT’s playing a new role 2011/12) Focused IO strategy to meet differential targets (IO 2010/11) Strategic review of international recruitment targets linked to Development Plans (Planning Office, SR Team 2010/11) |  |  |  |
|  |  | Funding Inappropriate fee structure | Benchmark fees, scholarships and bursaries against those of competitors |  | Strategic review of international recruitment costs in relation to income (IO 2010/11) |  |  |  |
|  |  | International Student Support Limited and uncoordinated international student support | Rapid response to student surveys incl. PTES Responsive LSU and Student Support Centre Support work of Graduate School |  |  |  |  |  |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Unpredictable Issues Sudden unexpected changes e.g. currency fluctuations, terrorism, visa problems New PBS visa system and Tier 4 status Impact of recession overseas | Effective modelling of intakes and use of shadow intakes in budgeting Regular country specific analysis |  | Close monitoring and evaluation of impact of PB visa system (IO 2010/11 & 2011/12) |  |  |  |
| c) Failure to attract well qualified students (Strategic) | 3,4 | Staff See risk e) below |  | 3,3 |  | Profile raising: good NSS results September 2011 | 3,3 | Overall assessment of risk & response: Date of review: 9 June 2011 |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Visibility & Image Declining position in league tables Reputational problems associated with UG and PG admissions processes | Focused admissions policy addressing applicants’ expectations Continued increase in UG entry grades as appropriate Continue to respond quickly to results of student surveys incl NSS |  | Promote clearly University successes using a range of media (Registry/Markt. & Comm. 2010/11) Further develop links with high achieving schools in UK and overseas in partnership with the International Office (Acad Registry/Schools 2011/12) | Work is underway to check tariff score for league tables to assess how it is calculated and whether the score is accurately displayed |  |  |
|  |  | Marketing and Student Demand Increasingly aggressive competition in UK & overseas for high quality students | Judicious use of scholarships Regular evaluation of UG and PG programmes Promotion of student learning opportunities in and beyond the curriculum in line with L & T and Internationalisation Implementation Plans |  |  |  |  |  |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Student support Infrastructure See risk g) below |  |  |  |  |  |  |
| d) Poor internal and external evaluations of teaching quality and learning support (Strategic) | 4,3 | Staff See risk e) below |  | 3,2 |  |  | 3,2 | Overall assessment of risk & response: Date of review: 9 June 2011 |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Quality Assurance & Enhancement Failure to take account of statutory requirements, QAA academic infrastructure, or professional body accreditation requirements Failure to observe internal quality assurance procedures (Operational) Failure to engage in development-led quality enhancements (Operational) Insufficiently rigorous procedures for major learning and teaching projects Major changes in University structure resulting in failure of current QA systems | Clear strategy and operational plan for teaching and learning and assessment Effective PQ Team, with awareness of external context and willingness to consult within the institution Efficient and effective annual and periodic review process Regular Dept. review of programmes Regular review of NSS findings Rigorous student feedback process |  | Reorganise internal QA systems in response to changes in University structure (PVC(T), PQ Team 2010/11) | QAA audit preparation – new method (2011/12) Discuss enhanced student feedback processes with LSU (PVC(T), Teaching Centre, Registry, LSU – 2011) Integrate e-learning team with Teaching Centre and promote support to Schools (2011) |  |  |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Student Support Infrastructure Poor learning & teaching facilities Insufficient investment to keep pace with developments and competitors Major changes in University structure resulting in disruption of student support mechanisms at departmental level | Regular review & improvement of teaching accomm. Pro-active teaching and learning support services |  | Continue to progress learning spaces project (Director of Change Projects/LTC/Facilities Management 2010/11) Ensure that QA and student support responsibilities clearly located within new structures (PVC(T) 2010/11) |  |  |  |
|  |  | Published information Failure to ensure that published teaching and learning information is accurate and fit for purpose (Operational) | Responsibility for publications vested in a limited number of staff |  | Content management system being developed (Director, Marketing and Communications 2010/11) | Provide public information in response to consultation (Acad Registry 2011) |  |  |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| e) Insufficient engagement by staff in teaching in relation to priorities in research and enterprise (Strategic) | 3,3 | Inability to attract and retain quality staff System of staff recognition and reward that does not consider adequately scholarship in teaching and learning Perceived problems of communication between staff and students | Focused staff recruitment, development and retention policies Effective probation system including appropriate teaching and learning support Staff research built into learning and teaching opportunities for students Regular monitoring of new criteria for SL promotion | 3,2 | Evaluate re-accredited New Lecturers’ Course (Teaching Centre 2010/11) Evaluate Communicate project to enhance communication/presentation skills of staff (Teaching Centre 2010/11) Professorial promotion criteria being modified (2010/11) | SBE enterprise hub to be launched (SBE 2010/11 & 2011/12) Promote Student Charter (LTC/Marketing/Comms 2011) | 3,2 | Overall assessment of risk & response: Date of review: 9 June 2011 |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| f) Failure to protect University’s intellectual property interests and its reputation through its learning materials, including their conflation with third-party owned materials, e.g. as Open Educational Resources (OER) Failure to respect third party IPR when sourcing, editing, aggregating and using physical and online learning materials, including text, images, audio and video, to support Loughborough programmes | 3,3 | Lack of effective advice for staff Lack of resourcing to provide effective advice Lack of staff awareness of issues relating to he use of external Web 2.0 services where there is no service level agreement with the University No OER policy or failure to communicate it clearly to staff Insufficient quality checking of OER Some academic staff do not have the time or inclination to give serious consideration to IR issues relating to learning and teaching Academic staff may not be receiving clear directives from Heads of Department/Deans that they need to take IPR seriously The copyright clause (21) in Conditions of Service iconfusing and potentially misleading, because the exceptions listed under paragraph 2 suggest that academics own copyright in relation to teaching materials VLE containing materials that have been created by academics while they were employed by other institutions; other institutional VLEs containing materials created by staff who have moved on from LU Historicaly this has been overlooked in the sector The proliferation of Web 2.0 services and other online tools makes inadvertent copyright infringement more likely than it has ever been before | Access to learning materials by Loughborough students is normally restricted physically via attendance at lectures on campus, or virtually via authentication to Learn and associated systems New copyright officer post in Library has been agreed Web 2.0 guidance been developed | N/A |  | Induction and training for all academic and learning support staff in copyright issues (responsibility to be determined) Minority of learning materials made available under OER as a result of specific University decision to allow this (ELAG) Additional checks to ensure sufficient OER quality and no third party materials used without copyright clearance (Head of E-learning with Marketing and Communications) Effective dissemination of University policy on OER, including the publishing of content through high-profile channels including iTunesU, YouTube and JORUM Vice-Chancellor’s message to all HODs/HOSSs relating to the importance of copyright sent out on 15 July 2009 could be updated and resent to Denas, ADTs, Operations managers Copyright clause in Conditions of Service being modified in relation to key learning and teaching materials (HR 2011) | 3,2 | Overall assessment of risk & response: Date of review: 9 June 2011 |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| g) Insufficient investment to keep pace with developments and competitors (Strategic) | 4,4 | Student Support Infrastructure Poor teaching facilities Limited investment in IT and broader L&T infrastructure Fragmented student support services | Regular review of and investment in information systems, and physical infrastructure Pro-active teaching and learning support services Co-ordinated student support services . | 3,3 | Continue to progress learning spaces project (Director of Change Projects/LTC/Facilities Management 2010/11) Continue strategic development of e-learning (ELAG 2010/11) | Review outstanding needs for informal learning spaces (2011) | 3,3 | Overall assessment of risk & response: Date of review: 9 June 2011 |

3. Learning and Teaching												Responsibility: PVC(T)

| The Risk | Gross Risk | Factors that could relate to, or contribute towards the risk occurring | Current mitigating actions | Net Risk July 2010 | Improvement actions to mitigate the risk/person responsible | Action Arising – DATE of implementation | Change of rating achieved following implementation of action – Latest assessment | Annual review of Reporting Body L&TC |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| h) Engaging in collaborative provision without due diligence (Strategic) | 4,3 | Problems in relation to academic quality and standards or reputation at partner institutions Political Instability | Rigorous procedures for assuring quality and standards of collaborative provision Strengthened Programme Quality and Partnerships section in Registry Regular liaison with BUE senior staff Rigorous monitoring and review processes by LU and BUE Support BUE with staff recruitment as appropriate | 4,2 | Review teaching implications of OPLC (2011) Major projects launched at BUE supported by Director of Internationalisation Strategy (2011) |  | 4,2 | Overall assessment of risk & response: Date of review: 9 June 2011 |

3. Learning and Teaching												Responsibility: PVC(T)

Last reviewed by ELT Risk Sub Group:   10 February 2011

I confirm that

a)	all operations controls are functioning

- the risk is appropriate

- any near misses/incidents since last appearance at ELT are detailed overleaf

Signature…………….………………………………………

(PVC Teaching)

Date:…………………………………………………………

Last amended:  May 2010