Loughborough University

University Strategy 2006-2016

Implementation Planning Priorities 2011/12

| Learning & Teaching |  |
| --- | --- |
| Priorities | Progress |
| Student Recruitment, Admissions, Outreach and Fair Access |  |
| Review intakes/populations Instigate new governance arrangements for Student Recruitment and Admissions Conduct major review of student populations and intakes across Schools for forward planning Agree intake targets with Schools for 2012/13 across major categories with continued emphasis on intake quality Implement action plan for EU and international recruitment, including PGRs, in light of strategic review across Schools Introduce application fee for PGT courses in the School of Business and Economics Monitor changes to Tier 4 PBS and implement appropriate amendments to systems and processes Consider scope for further central processing of student applications | Governance arrangement in place; modifications will be made at strategic level in 12/13 Population/intakes review ongoing; it will be informed by recruitment and admissions experience for 2012, notably in relation to UG UK/EU students Entry requirements increased at ABB/AAB boundaries for selected UG programmes. Work on equivalence table in 10/11 for PGT entry improved information for UK/EU and international applicants International recruitment plans developed in coordination with Schools to enhance diversification of international students, which includes entry into new markets e.g. Mexico, Botswana, Brazil. Supported new articulation agreements and engagement with overseas government funding bodies Application fee at PGT level in SBE successfully introduced and desired outcomes being achieved Electronic issue of CAS and changes to English language requirements successfully introduced as part of Tier 4 PBS compliance On central processing, position remains unchanged on 10/11 |
| Agree objectives and monitor actions of Student Outreach and Recruitment (SOAR) Team Develop a University-wide outreach, fair access and recruitment strategy in relation to Access Agreement and intake objectives Evaluate progress against approved strategic and operational objectives Develop SOAR team to incorporate three strands – outreach, recruitment /fair access and administration Instigate Marketing, Recruitment and Access Strategy Group and develop links with Marketing and Communications at a strategic level; involve Graduate School in PGT programme promotion linked to strategic priorities; work with Schools to ensure coordinated approach to initiatives Monitor progress of IFP with Loughborough College | High level strategy drafted; further work needed Access Agreement proposals for 12/13 agreed with Schools and relevant Support Services, and submitted to Operations Committee. Evaluation and targeting of activity being embedded Integrated SOAR team developing effectively with clear strands and areas of responsibilities. Significant links built up with high performing secondary schools Strategy Group functioning with membership across recruitment, admissions, IO, marketing and communications. Greater clarity of remit needed between strategic and operational matters Graduate School input provided to PGT programme categorization and promotion Recruitment growing to IFP; 3 semester model approved to enhance recruitment |
| Promote increasing cooperation between UG and PGT admissions teams in order to create a single integrated resource in 2012 Develop wholly electronic UCAS applications system: continue to scope project and design system in 11/12, for piloting in 12/13, and full implementation in 13/14 Develop a buddying system to encourage integration between undergraduate and postgraduate taught admissions teams Review processes to streamline and thus enable an increased speed of processing and improved customer service | UG electronic admissions system delayed at end of 2011 to await outcome of UCAS Admissions Process Review. Work now on track to operate a pilot system with selected Schools/Departments in 12/13 with anticipated implementation of full system for all in 13/14 Several UG and PGT staff have experience of working across both admissions systems, and it is planned to increase cross-system working in 12/13 PGT processes have been streamlined and IT developments introduced to speed up processing times and improve service to applicants and Schools. UG processes have also been streamlined, although additional work required in relation to AAB+/SNC has offset the benefits |
| Academic Curriculum Profile |  |
| Student Charter Launch Charter and review with Schools at end of academic year Ensure public information (Key Information Sets) at programme level etc. is clear and complete Agree with Schools key messages relating to LU’s academic provision and promote through range of media | Progress made at institutional and School levels in promoting and developing Charter Detailed work carried out in preparation for release of KIS Some progress made in developing key messages with formation of Operational Teams; recent investment in web developers and marketing officers linked to Schools will assist |
| UG programme review Evaluate UG programmes with Schools in context of higher fees paying particular attention to indicators of student demand, intake grades, Fair Access, and programme quality etc Ensure actions are taken as appropriate in relation to LSU survey and student feedback | Work begun with Schools to evaluate UG programmes through preparation of profile data and discussions in Operational Teams; further work needed in 12/13, including at PG level Actions underway in relation to Our Lufbra Survey (See progress report to Senate and Council on Strategic Planning Update, July ‘12) Student module feedback processes reworked and approved by Senate, March 2012 |
| Student Learning Opportunities |  |
| International learning Raise profile of international/global perspectives in the curriculum Monitor range of initiatives linked to international learning and strengthen links with LSU ‘Experience the World’ campaign, should it continue (see also Internationalisation Implementation Plan) | Limited progress in 2011/12. This area will be a priority in 12/13 |
| Enterprise Education Support cross-campus work of new Glendonbrook Centre for Enterprise Education | Glendonbrook Centre designing specialist enterprise outreach activity with support from SOAR. Teaching Centre and Careers staff working with GC |
| Placements Build on work carried out in 10/11; Conduct feasibility study/change project in relation to placements with the aim of ensuring that from 2012 entry, all UG students have the opportunity to undertake a study or work placement Seek to establish UG placement and graduate internship scheme as annual initiative | Feasibility study complete: recommendations approved by Senate; implementation of agreed actions underway Operations Committee approved placement and internship scheme as annual initiative |
| External organizations, student opportunities and higher fees Build on work carried out in 10/11 with Careers and Employability Centre (CEC) and Enterprise Office etc - further develop initiatives with key external partner organisations designed to offer a range of opportunities to UG students linked to higher fees (eg. sponsorship etc); ensure these initiatives are integrated as part of broader partnership development work | Interactions with employers continue to highlight openings for further engagement eg. on projects linked to degree programmes. Discussions between Enterprise Office and CEC on-going with regard to sharing contacts, and developing a client relationship management system |
| Employability opportunities beyond curriculum Expand opportunities for UG and PG students to support outreach and fair access in line with Access Agreement Continue to enhance Loughborough graduate and postgraduate prospects through initiatives led by CEC including mentoring, work shadowing, workshops offered by key employers Pilot PGT Employability Award Monitor participation in and completion of UG Employability Award (See also Student Experience Implementation Plan) | Discussions underway between SOAR and LSU to develop a coordinated approach to student involvement in fair access initiatives CEC developed proposals for establishment of Professional Work Experience Unit to coordinate and enhance UG, graduate and PG employability opportunities, and to oversee Employability Award SBE participated in initial pilot of PGT Employability Award; pilot will be extended for a further year |
| Student Learning Resources and Support |  |
| Induction Building on previous work, ensure induction initiatives with new students and returners are embedded and effective (See also Student Experience Implementation Plan) | Good progress made with University induction website; further work needed to ensure consistency in resources made available to students across campus |
| Student engagement Work with Schools to develop further strands of current Student Engagement project, and monitor for effectiveness | Progress made with a number of initiatives and summary/evaluation paper presented to Academic Standards and Procedures Sub-Committee, May 2012 |
| Academic and employability skills support Work with Schools to raise profile of institutional ‘skills’ support for students, including maths and statistics, and academic ‘literacy’ skills; Seek to embed in the curriculum as appropriate | Academic librarians increased number of bespoke sessions in Schools on academic skills within curriculum, including information and digital literacy. Take-up of academic practice online course increasing. Get the Know-How workshops remain popular. Overview of activities presented to LTC, June ‘12 |
| E-learning Consult Schools on new e-learning strategy and implementation plan Launch implementation process with Schools | Work underway with Schools to raise profile of E-learning Strategy and to take forward associated Implementation Plan |
| Learning spaces Agree institutionally, minimum IT presence in all pool rooms Invest Hefce Teaching Capital Fund appropriately eg. on provision of further informal learning spaces where there is a clear need and student demand | Teaching Support (FM) consulted staff and students on standards ‘expected’ in all pool rooms; outcomes to be used in investment decisions Major capital developments underway to benefit student learning, including University Library top floor and Brockington ground floor |
| Staff Support, Quality Assurance and Enhancement |  |
| Governance in learning and teaching Instigate new governance arrangements including appropriate student representation Evaluate effectiveness of committee and sub-committee structure | New governance arrangements in place Programme President system developing well at School level Modifications to governance under consideration for 12/13 Effectiveness of SSLCs under review including strength of student representation |
| QAA Audit Prepare for Institutional Audit (April/May) Ensure successful outcome | Audit preparations completed satisfactorily, including drafting of Institutional Self-Evaluation; Student Submission prepared with oversight by LSU; outcomes awaited |
| Review processes Introduce new APR and PPR processes and monitor effectiveness/efficiency Review placement module specs as part of APR | New APR/PPR processes implemented and under review for 12/13 Actions underway to ensure greater consistency in placement module specs |
| Quality enhancement Agree enhancement priorities for Teaching Centre in consultation with Schools, and deliver through bespoke initiatives | Range of initiatives developed, linked to strategic priorities and particular School needs. These include project on skills development with PHIR as part of review of UG curriculum; workshop on teaching large classes with SSEHS and open session on supporting international students |
| Central support for staff Ensure Schools are aware and take advantage of the different strands of central support in relation to learning and teaching | Good links developing between Teaching Centre, CEDE and Glendonbrook Centre; complementarity of activities to be worked on and promoted internally |
| Staff Recognition and Reward |  |
| Probation arrangements Evaluate reaccredited New Lecturers’ course with first cohort of completers | Evaluation underway |
| Promotions and Awards Evaluate teaching section of SL promotions with feedback from candidates, HoDs and ADTs on first 4 rounds; introduce refinements as appropriate Revised criteria for personal chairs to be implemented Launch new University Award for Outstanding Contribution to Research-informed Teaching | Evaluation underway of teaching section of SL promotions Revised personal chair criteria in use New Award launched June 2012 |